## Time line
Rute-Kunjungan | Timeline
| 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28
Bandung (Dalam Kota)
Kab. Bandung, Garut, Cililin
Subang, Majalengka, Cirebon, Kuningan
Bogor, Depok, Tangsel
Bekasi, Cikarang, Karawang, Purwakarta, Rengasdengklok
Sukabumi, Pel. Ratu, Cianjur
Catatan:
: Joint Visit dgn Inficlo
: Visit mandiri karena Inf sudah kunjungan

## Mapping Kunjungan Pelanggan
MAPPING KUNJUNGAN PELANGGAN
NO | NAMA PELANGGAN | KATALOG | ALAMAT | KETERANGAN
1 | BANDROS | POLOS | BANDUNG | DONE
2 | ATLANTIS | POLOS | BANDUNG | DONE
3 | TAUFIK ST | POLOS | BANDUNG | DONE
4 | DEDI KURNIADI | POLOS | BANDUNG | DONE
5 | INDRA FASHION | POLOS | BANDUNG | DONE
6 | IMAS JUBAEDAH | POLOS | BANDUNG | Kunjungan Senin/Selasa
7 | AYU FITRI | POLOS | RENGASDENGKLOK | Visit Week 3
8 | RUSLI-GLOBAL | POLOS | BOGOR | Week 2 Agus join Inf
9 | YOSSI RAHMAWATI TANGSEL | 100% | TANGSEL | Week 2 Agus join Inf
10 | DEDE SAEPUL MILAH | 100% | PURWAKARTA | Visit Week 3
11 | YAYAT HIDAYAT | 100% | TANGSEL | Week 2 Agus join Inf
12 | ARIF RAHMAN HAKIM | 100% | DEPOK | Week 2 Agus join Inf
13 | PP - PRIMA PERKASA | 100% | BANDUNG | Kunjungan Senin/Selasa
14 | KUSNO | 100% | BANDUNG | Kunjungan Senin/Selasa
15 | ELVANA JAYA - AANG | 80/100 | PURWAKARTA | Visit Week 3
16 | SARIP HIDAYAT-KARAWNG | 80/100 | KARAWANG | Visit Week 3
17 | JENAL ARIPIN (KARAWANG) | 80/100 | KARAWANG | Visit Week 3
18 | ARIS PUJIONO | 80/100 | KARAWANG | Visit Week 3
19 | ADI RIYADI | 80/100 | KARAWANG | Visit Week 3
20 | RIDWAN FAUZI ¦ ODON | 80/100 | PEL. RATU | Visit Week 4
21 | WAWAN GUNAWAN | 80/100 | KARAWANG | Visit Week 3
22 | SANUSI - BABAKAN CIPARAY | 80/100 | BANDUNG | Kunjungan Senin/Selasa
23 | PT AZALEA SEJAHTERA MANDIRI | 100/100 | CIKARANG | Visit Week 3
24 | AGUS ANDRIANTO | 100/100 | PEL. RATU | Visit Week 4
25 | YOSSI RAHMAWATI TANGSEL | 100/100 | TANGSEL | Week 2 Agus join Inf
26 | CV. BENTANG FASHION | 100/100 | SUKABUMI | Visit Week 4
27 | MULYANA - PAMULANG | 100/100 | TANGSEL | Week 2 Agus join Inf
28 | RENDY - SUBANG | 100/100 | SUBANG | Include Visit Inf Minggu ini
29 | IWAN HERMAWAN - CIPETIR | 100/100 | KAB. BANDUNG | Awal Bulan
30 | DEDE MULYADI ¦ PAMULANG | 100/100 | TANGSEL | Week 2 Agus join Inf
31 | NURYANA ¦ UJB CIMAJA | 100/100 | PEL. RATU | Visit Week 4
32 | CAYOTO | 100/100 | CIKARANG | Visit Week 3
33 | AJAT ¦ PATI JAYA ABADI | 100/100 | PEL. RATU | Visit Week 4
34 | IWAN ¦ PELABUHAN RATU | 100/100 | PEL. RATU | Visit Week 4
35 | MAYA SMJ (SETIA MEKAR JAYA) | 100/100 | BANDUNG | Kunjungan Senin/Selasa
36 | UJANG SURYATNA | 100/100 | SUKABUMI | Visit Week 4
37 | RUSLI-GLOBAL 2 | 100/100 | BOGOR | Week 2 Agus join Inf
38 | FEBRIANSYAH | 100/100 | CIREBON | Include Visit Inf Minggu ini
39 | LUKMANUL HAKIM | 100/100 | PEL. RATU | Visit Week 4
40 | SITI AISYAH - JAJANG | 100/100 | BANDUNG | Kunjungan Senin/Selasa
41 | CENGCENG MISBAH ¦ HDR | 100/120 | CIANJUR | Visit Week 4
42 | DIRWAN | 100/120 | BANDUNG | Kunjungan Senin/Selasa
43 | ECE SURYADI | 100/120 | PEL. RATU | Visit Week 4
44 | NILAM COLLECTION | 100/120 | CIKARANG | Visit Week 3
45 | RIANA YUSUF | 100/120 | SUKABUMI | Visit Week 4
46 | RINA BAESUNI / BP. NURSIN | 100/120 | TANGSEL | Week 2 Agus join Inf
47 | SAEPUL MUNAWAR | 100/120 | GARUT | Awal Bulan
48 | YUSUP SOLEHUDIN | 100/120 | MAJALENGKA | Include Visit Inf Minggu ini
49 | AHMAD ASPURI | 100/120 | MAJALENGKA | Include Visit Inf Minggu ini
50 | ASEP JENAL M - SUBANG | 100/120 | SUBANG | Include Visit Inf Minggu ini
51 | ASEP JENAL M - SUKABUMI | 100/120 | SUKABUMI | Visit Week 4
52 | MEKI SANDI ROLIANSYAH | 100/120 | DEPOK | Week 2 Agus join Inf
53 | AL MUMTAZ - ASEP JUNAIDI | 100/120 | GARUT | Awal Bulan
54 | IWAN HERMAWAN - CIPETIR | 100/120 | CILILIN | Awal Bulan
55 | YANYAN HERYANA | 100/120 | SUKABUMI | Visit Week 4
56 | IVAN SETIAWAN | 100/120 | CIKARANG | Visit Week 3
57 | FEBRIANSYAH | 100/120 | CIREBON | Include Visit Inf Minggu ini
58 | ATANG SETIAWAN - RAGELL | 100/120 | KARAWANG | Visit Week 3
59 | RINTO SUGIANTO | 100/120 | SUKABUMI | Visit Week 4
60 | MISBAH (INDAH JAYA) | 100/120 | SUKABUMI | Visit Week 4
61 | BOJES KUNINGAN | 100/170 | KUNINGAN | Include Visit Inf Minggu ini
62 | ZOE - SAUYUNAN MAS | 100/170 | BANDUNG | Kunjungan Senin/Selasa
63 | NANDAR SOLEH | 100/170 | GARUT | Awal Bulan
64 | SANDI SANJAYA | 100/170 | SUKABUMI | Visit Week 4
65 | AMAR SOLEH | 100/170 | GARUT | Awal Bulan
66 | ASEP FAHMI (DIAN JAYA) | 100/170 | TANGSEL | Week 2 Agus join Inf
67 | TRISAL AL-HASAN - MANDIRI JAYA | 100/170 | SUKABUMI | Visit Week 4
68 | ENDAH ISKANDAR ¦ JAYA MANDIRI BDG | 100/180 | BANDUNG | Kunjungan Senin/Selasa
69 | MISBAH - CIBUNTU | 100/180 | KARAWANG | Visit Week 3
70 | PURNAMA GANJAR | 100/180 | BANDUNG | Kunjungan Senin/Selasa
71 | LEDI PUTRA MANDIRI (LPM) | 100/180 | BEKASI | Visit Week 3
72 | HERDI FALS | 100/180 | PEL. RATU | Visit Week 4
73 | AL MUMTAZ - ASEP JUNAIDI | 100/180 | GARUT | Awal Bulan
74 | UJANG DARMIN | 100/180 | PEL. RATU | Visit Week 4
75 | JAYA MANDIRI ¦ ASEP RADJIS | 100/180 | SUKABUMI | Visit Week 4
76 | MUSTAMA ¦ FAJAR MULYA | 100/180 | CIANJUR | Visit Week 4

## Plan Distribusi Katalog
| PO KATALOG KUZATURA |  |  | PO KATALOG INFIKIDS
| POLOS | 2500 |  | POLOS | 2500
| 100% | 1500 |  | 100% | 1500
| 80/100 | 1000 |  | 80/100 | 1000
| 100/100 | 3000 |  | 100/100 | 3000
| 100/120 | 3000 |  | 100/120 | 3000
| 100/170 | 1000 |  | 100/170 | 1000
| 100/180 | 2500 |  | 100/180 | 2500
NO | NAMA PELANGGAN | KATALOG | INFIKIDS | KUZATURA | JUMLAH | SISA STOCK INFIKIDS | SISA STOCK INFIKIDS
1 | BANDROS | POLOS | 50 | 50 | 100 | 750 | 750
2 | ATLANTIS | POLOS | 100 | 100 | 200
3 | TAUFIK ST | POLOS | 100 | 100 | 200
4 | DEDI KURNIADI | POLOS | 50 | 50 | 100
5 | INDRA FASHION | POLOS | 50 | 50 | 100
6 | IMAS JUBAEDAH | POLOS | 200 | 200 | 400
7 | AYU FITRI | POLOS | 100 | 100 | 200
8 | RUSLI-GLOBAL | POLOS | 100 | 100 | 200
9 | RETAIL | POLOS | 1000 | 1000 | 2000
10 | YOSSI RAHMAWATI TANGSEL | 100% | 100 | 100 | 200 | 400 | 400
11 | DEDE SAEPUL MILAH | 100% | 200 | 200 | 400
12 | YAYAT HIDAYAT | 100% | 100 | 100 | 200
13 | ARIF RAHMAN HAKIM | 100% | 100 | 100 | 200
14 | PP - PRIMA PERKASA | 100% | 50 | 50 | 100
15 | KUSNO | 100% | 50 | 50 | 100
16 | RETAIL | 100% | 500 | 500 | 1000
17 | ELVANA JAYA - AANG | 80/100 | 300 | 300 | 600 | 350 | 350
18 | SARIP HIDAYAT-KARAWNG | 80/100 | 50 | 50 | 100
19 | JENAL ARIPIN (KARAWANG) | 80/100 | 50 | 50 | 100
20 | ARIS PUJIONO | 80/100 | 50 | 50 | 100
21 | ADI RIYADI | 80/100 | 50 | 50 | 100
22 | RIDWAN FAUZI ¦ ODON | 80/100 | 50 | 50 | 100
23 | WAWAN GUNAWAN | 80/100 | 50 | 50 | 100
24 | SANUSI - BABAKAN CIPARAY | 80/100 | 50 | 50 | 100
25 | PT AZALEA SEJAHTERA MANDIRI | 100/100 | 300 | 300 | 600 | 0 | 0
26 | AGUS ANDRIANTO | 100/100 | 300 | 300 | 600
27 | YOSSI RAHMAWATI TANGSEL | 100/100 | 200 | 200 | 400
28 | CV. BENTANG FASHION | 100/100 | 500 | 500 | 1000
29 | MULYANA - PAMULANG | 100/100 | 300 | 300 | 600
30 | RENDY - SUBANG | 100/100 | 100 | 100 | 200
31 | IWAN HERMAWAN - CIPETIR | 100/100 | 100 | 100 | 200
32 | RIZKI MAULANA MALIK | 100/100 | 50 | 50 | 100
33 | DEDE MULYADI ¦ PAMULANG | 100/100 | 100 | 100 | 200
34 | NURYANA ¦ UJB CIMAJA | 100/100 | 100 | 100 | 200
35 | CAYOTO | 100/100 | 100 | 100 | 200
36 | AJAT ¦ PATI JAYA ABADI | 100/100 | 100 | 100 | 200
37 | IWAN ¦ PELABUHAN RATU | 100/100 | 50 | 50 | 100
38 | MAYA SMJ (SETIA MEKAR JAYA) | 100/100 | 50 | 50 | 100
39 | UJANG SURYATNA | 100/100 | 100 | 100 | 200
40 | YAYAN HERYANA | 100/100 | 100 | 100 | 200
41 | FEBRIANSYAH | 100/100 | 200 | 200 | 400
42 | LUKMANUL HAKIM | 100/100 | 100 | 100 | 200
43 | RUSLI-GLOBAL 2 | 100/100 | 100 | 100 | 200
44 | SITI AISYAH - JAJANG | 100/100 | 50 | 50 | 100
45 | CENGCENG MISBAH ¦ HDR | 100/120 | 100 | 100 | 200 | 300 | 300
46 | DIRWAN | 100/120 | 200 | 200 | 400
47 | ECE SURYADI | 100/120 | 100 | 100 | 200
48 | NILAM COLLECTION | 100/120 | 300 | 300 | 600
49 | RIANA YUSUF | 100/120 | 50 | 50 | 100
50 | RINA BAESUNI / BP. NURSIN | 100/120 | 50 | 50 | 100
51 | SAEPUL MUNAWAR | 100/120 | 100 | 100 | 200
52 | YUSUP SOLEHUDIN | 100/120 | 100 | 100 | 200
53 | AHMAD ASPURI | 100/120 | 100 | 100 | 200
54 | ASEP JENAL M - SUBANG | 100/120 | 300 | 300 | 600
55 | ASEP JENAL M - SUKABUMI | 100/120 | 100 | 100 | 200
56 | MEKI SANDI ROLIANSYAH | 100/120 | 200 | 200 | 400
57 | AL MUMTAZ - ASEP JUNAIDI | 100/120 | 300 | 300 | 600
58 | IWAN HERMAWAN - CIPETIR | 100/120 | 100 | 100 | 200
59 | YANYAN HERYANA | 100/120 | 100 | 100 | 200
60 | IVAN SETIAWAN | 100/120 | 100 | 100 | 200
61 | FEBRIANSYAH | 100/120 | 200 | 200 | 400
62 | ATANG SETIAWAN - RAGELL | 100/120 | 100 | 100 | 200
63 | RINTO SUGIANTO | 100/120 | 50 | 50 | 100
64 | MISBAH (INDAH JAYA) | 100/120 | 50 | 50 | 100
65 | BOJES KUNINGAN | 100/170 | 200 | 200 | 400 | 50 | 50
66 | ZOE - SAUYUNAN MAS | 100/170 | 100 | 100 | 200
67 | NANDAR SOLEH | 100/170 | 50 | 50 | 100
68 | AGUS DEPRIANTO | 100/170 | 50 | 50 | 100
69 | SANDI SANJAYA | 100/170 | 100 | 100 | 200
70 | AMAR SOLEH | 100/170 | 50 | 50 | 100
71 | ASEP FAHMI (DIAN JAYA) | 100/170 | 300 | 300 | 600
72 | TRISAL AL-HASAN - MANDIRI JAYA | 100/170 | 100 | 100 | 200
73 | ENDAH ISKANDAR ¦ JAYA MANDIRI BDG | 100/180 | 500 | 500 | 1000 | 400 | 400
74 | MISBAH - CIBUNTU | 100/180 | 300 | 300 | 600
75 | PURNAMA GANJAR | 100/180 | 200 | 200 | 400
76 | LEDI PUTRA MANDIRI (LPM) | 100/180 | 100 | 100 | 200
77 | HERDI FALS | 100/180 | 50 | 50 | 100
78 | AL MUMTAZ - ASEP JUNAIDI | 100/180 | 400 | 400 | 800
79 | UJANG DARMIN | 100/180 | 50 | 50 | 100
80 | JAYA MANDIRI ¦ ASEP RADJIS | 100/180 | 400 | 400 | 800
81 | MUSTAMA ¦ FAJAR MULYA | 100/180 | 100 | 100 | 200